## Sheet1
| 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | Complete |  | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23
Motor Driver Implementation | [14 empty] | Target | Motor Driver Implementation | bar: 2026-01-15 to 2026-01-22
Add a way to save pathways taken | [14 empty] | Behind | Add a way to save pathways taken | bar: 2026-01-22
Redesign Anchor and FOB PCBs | [14 empty] | In Progress | Sensor testing with Controls Sub | bar: 2026-01-22 to 2026-01-29
Distance and Direction measurements | [15 empty] | Redesign Anchor and FOB PCBs | bar: 2026-01-22
Show the path taken when user logs out | [15 empty] | Distance and Direction measurements | bar: 2026-01-29
Have faster user location/distance updates | [15 empty] | Show the path taken when user logs out | bar: 2026-01-29
Motor driver and controls integration | [15 empty] | Have faster user location/distance updates | bar: 2026-01-29 to 2026-02-05
ESP sensor integration | [15 empty] | UWB and ESP integration | bar: 2026-02-05
UWB and ESP integration | [15 empty] | ESP sensor integration | bar: 2026-02-05 to 2026-02-12
App and ESP comms integration | [15 empty] | Motor driver and controls integration | bar: 2026-02-12 to 2026-02-19
Sensor testing with Controls Sub | [15 empty] | App and ESP comms integration | bar: 2026-02-12 to 2026-02-19
Weight detection platform | [15 empty] | Weight detection platform | bar: 2026-02-19 to 2026-02-26
Full rover subsystem integration Test | [15 empty] | Full rover subsystem integration Test | bar: 2026-03-05 to 2026-03-19
System Validation | [15 empty] | System Validation | bar: 2026-03-26 to 2026-04-02
Final Demo | [15 empty] | Final Demo | bar: 2026-04-23
Complete
Target
Behind
[16 empty] | Timeline | subsystem |  |  | Integration |  | Blitz | fix issues with integration | demo integration | spring break | system test | system validation | demo prep | final pres | final pres | Final Demo
Motor Driver Implementation
Add a way to save pathways taken
Redesign Anchor and FOB PCBs
Distance and Direction measurements
Show the path taken when user logs out
Have faster user location/distance updates
Sensor testing with Controls Sub
UWB and ESP integration
ESP sensor integration
Motor driver and controls integration
App and ESP comms integration
Weight detection platform
Full rover subsystem integration Test
System Validation
Final Demo